## Cover
Template
TEST CASE
| Project | FunixPricingChain
Version

## Test case List
TEST CASE LIST
Project Name
Test Environment Setup Description |  | <List environment requires in this system 1. Localhost 2. Web Browser 3. Metamask 4. hardhat develop >
No | Function Name | Sheet Name | Description | Pre-Condition
1 | create new pricing session | Admin | create new pricing session | required product name and description, images are optional
2 | register | Admin, Participant | sign up | have not registered before
3 | update user detail | Participant | change user detail(name, email) | registered only
4 | get sessions | Admin, Participant | get available sessions | connected and registered
5 | propose | Participant | propose price | connected and registered, session is in "OPENED" state and not timeout
6 | after closing session | Admin | set final price, update participant deviation and # joined session | session is in "OPENED" state
7 | get all users detail | Admin | get all users information
8 | update session detail | Admin | change session detail (name, description, images) | session is in "OPENED" state

## Admin
Module Code | Admin Functions | [7 empty] | Pass
Test requirement | Connected to Dapp with admin address via metamask | [7 empty] | Fail
Req ID | [8 empty] | Untested
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | NA
6 | 0 | 0 | 0 | 6
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Actual Output | Result | Test date | Note
Register
Admin-0.1 | sign up | 1. Connect to the Dapp with metamask 2. Redirected to the register page (automatically) 3. fill in the required information | Admin is registered | Have not registered before | Admin is registered | PASS | 2022-09-06
Create new session
Admin-1.1 | create new session | 1. Connect to the Dapp with metamask with Admin address 2. Click "Create New Session" button on Navbar 3. Fill in product name, description, images (optional) | A new session will be added to the sessions list then redirect to the sessions page | product name and description must be filled | new session is created and displayed on sessions page | PASS | 2022-09-06
Get sessions
Admin-2.1 | get available sessions | 1. Conenct to the Dapp with metamask | All sessions should be displayed on sessions page |  | All sessions are dispayed | PASS | 2022-09-06
Get users list
Admin-3.1 | get all users | 1. Connect to Dapp with Metamask with Admin address 2. Navigate to "Accounts" pages by clicking on Accounts button on navbar | All users information should be displayed on accounts page |  | All users are dispayed | PASS | 2022-09-06
Change session detail
Admin-4.1 | Change session detail | 1. Connect to Dapp with Metamask with Admin address 2. Choose a session to change the information 3. Click "Update Session Detail" button and then fill in the name, description, images(if available) then confirm the transaction | New detail about the session should be updated | Session must in "OPENED" state | Detail are updated | PASS | 2022-09-06
After closing session
Admin-6.1 | Set final price | 1. Connect to Dapp with Metamask with Admin address 2. Choose a session to set final price 3. Fill in the final price and click submit button then confirm the transaction | Final price of the session is stored and state of the session changes to "CLOSED" and deviation, # of joined sessions of participants who joined the session should be updated | Session must in "OPENED" state | State is changed to "CLOSED" and final price of the session is stored and deviation as well as # of joined sessions of participants who joined are updated | PASS | 2022-09-06
Note on G8: Pass Fail Untested N/A

## Participant
Module Code | Participant Functions | [7 empty] | Pass
Test requirement | Connect to the Dapp with metamask | [7 empty] | Fail
Req ID | [8 empty] | Untested
Pass | Fail | Untested | N/A | Number of Test cases |  |  |  |  | NA
4 | 0 | 0 | 0 | 4
ID | Test Case Description | Test Case Procedure | Expected Output | Inter-test case Dependence | Actual Output | Result | Test date | Note
Update Participant Info
Participant-1.1 | Update Participant Fullname and Email | 1. Connect to the Dapp with the metamask with registered address 2. Hover the mouse to account address on the top right corner of the page (rightmost of the navbar) then click "Account" button to access account information page. 3. Press "Change information" button then change the information and finally click "Submit" and confirm the transaction | Information is changed and stored to the blockchain | Need to be registered | The information is updated after changing | PASS | 2022-09-06
Register
Participant-1.2 | sign up new user | 1. Connect to the Dapp with the metamask 2. The website then automatically redirects to register page if the connected address has not sign up yet 3. Fill in detail then submit and confirm the transaction | New participant is stored | Connect address has not registerd yet | New participant is created | PASS | 2022-09-06
Get sessions
Participant-1.3 | View all avalable sessions | 1. Connect to the Dapp with the metamask. 2. Navigate to sessions | All sessions should be displayed | Need to be registered and connected | All sessions are displayed | PASS | 2022-09-06
Propose
Participant-1.4 | Propose price | 1. Connect to the Dapp with the metamask. 2. Choose a opened session 3. Fill in the proposed price 4. Submit then confirm the transaction | Propose price of the participant should be stored | Need to be registered and connected, session is still opened and not timeout if there is a sessionDuration | The proposed price is stored | PASS | 2022-09-06
Note on G8: Pass Fail Untested N/A

## Test Report
TEST REPORT
Project Name | FunixPricingChain |  | Creator
Notes
No | Module code | Pass | Fail | Untested | N/A | Number of test cases
1 | Admin Functions | 6 | 0 | 0 | 0 | 6
2 | Participant Functions | 4 | 0 | 0 | 0 | 4
| Sub total | 10 | 0 | 0 | 0 | 10
| Test coverage |  | 100 | %
| Test successful coverage |  | 100 | %